## Task List
d10x Tasklist | Platform/Details | Time lines | Team member | Remark
Project plan |  |  | Vikas
Lean/Agile approach |  |  | Shakeel
Data feed
Twitter | Github.kaggle,local,linux server,EAP |  | Akshya
Bloomberg/reuters | Github.kaggle,local,linux server,EAP |  | Akshya
google alert,reddit |  | 22/8 | Akshya
Time window ?
Streaming | EAP,local | 23/8 | Eklavya
Historical | EAP | 23/8 | Akshya
NLP Tasks
Load data in pandas or dataframes
Text processing
Noise removal
Stopword,URL,punctuation etc
Lemmatization
Stemming
Spelling correction | Text blob
Object standardization
Replace hashtag etc
Regula expression
Dependency Grammer
Speech tagging
NER | Entity disambiguation
Knowledge graph
Topic modelling
word embedding | word2vec
glove
Bert- OPTIONAL
CBOW
N-gram | Uni gram
Bi gram
trigram
Fake news detector
tf-idf | tokenize text to sentence
count vectorizer
Feature extraction
Syntactical parsing
POS tagging,dependency grammer
Entity parsing
Phrase detection
Freq/density function
Text matching
Levenshtein distance,Phonetic matching
Flexible string match,cosine similarity
nlp Features | Word count,CHAR Count of DOC
AVG WORD DENSITY
Freq list of POS tag
Noun count,verb count,adj count
adverb count,pronoun count
Text Rank algorithm
Generating Summary
Sort unverified tweets on the basis of Text Rank Score
Pick top tweets whose score is greater than threshold
Arrange tweets in the order they appear in original text
Split train test ,CV script
Build model - Explore | Supervised -text classification
Unsupervised-Lexicon based
SVM,ANOVA,
LDA
MLP
GBDT
Conditiional Random field
Hidden MM
Naïve Bayes
Others
Hyperparamter tuning
Metrics | MSE
AUC
Grid search CV
Confidence level
|  | 26/8/2019 |  | Final deadline
Second Phase After text processing
Optional
Words as Sequence
top k features
Embedding | Tagging vector
Explore Keras model | RNN
LSTM
GRU
CNN-RNN
UI/UX | n UI setup in local | 22/8 | Shiv | Need url to integrate with cit velocity
n Responsive app exploration
| n Data base setup | 23/8 | Shakeel
| n Heatmap, world map ,tweet connecting graph | 26/8
| Citi velocity integration meeting with Rohit Lohiya –CPT | 23/8 | Vikas | Ticket raised for qacit velocity access
Meeting with Simon |  | 27/8/2019 | All | Feedback
Mark/Andy
Feed back mechanism | Watchlist/Trader feedback | 29/8/2019 | Vikas | Create ML tuning model
Implementing changes | Based on trader's feedback | 30/8 | All | Sign off from Simon,Mark